## Weekly Report
As of Date: 2024/10/01
| 2024-06-01 |  | 2024-07-02 |  | 2024-08-02 |  | 2024-09-02 |  | 2024-10-03 |  | 2024-11-03 |  | 2024-12-04 |  | 2025-01-04 |  | 2025-02-04 |  | 2025-03-07 |  | 2025-04-07 |  | 2025-05-08 |  | 2025-06-08
TBOS System
wk ended | 2024-08-20 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-02-11 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11
Plan (weekly) | 0 | 3 | 7 | 10 | 12 | 10 | 8 | 11 | 9 | 9 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Result (weekly) | 0 | 3 | 7 | 9 | 13 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Difference (weekly) | 0 | 0 | 0 | -1 | 1 | 0 | 0 | -11 | -9 | -9 | -9 | -7 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan (accum.) | 0 | 3 | 10 | 20 | 32 | 42 | 50 | 61 | 70 | 79 | 88 | 95 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99
Result (accum.) | 0 | 3 | 10 | 19 | 32 | 42 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Difference (accum.) | 0 | 0 | 0 | -1 | 0 | 0 | 0 | -11 | -20 | -29 | -38 | -45 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49
| 2024-08-20 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-02-11 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11
Test Plan (weekly) | 0 | 0 | 0 | 0 | 27 | 210 | 120 | 92 | 89 | 101 | 133 | 34 | 0 | 0 | 0 | 0 | 0 | 0
Test Result (weekly) | 0 | 0 | 0 | 0 | 27 | 210 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test Plan (accum.) | 0 | 0 | 0 | 0 | 27 | 237 | 357 | 449 | 538 | 639 | 772 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806
Test Result (accum.) | 0 | 0 | 0 | 0 | 27 | 237 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357
Test Plan (remained) | 779 | 779 | 779 | 779 | 752 | 542 | 422 | 330 | 241 | 140 | 7 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27
Test Result (remained) | 779 | 779 | 779 | 779 | 752 | 542 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422
Inc Detected | 0 | 0 | 0 | 0 | 5 | 33 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inc Fixed | 0 | 0 | 0 | 0 | 5 | 33 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inc Detected (accum.) | 0 | 0 | 0 | 0 | 5 | 38 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
Inc Fixed (accum.) | 0 | 0 | 0 | 0 | 5 | 38 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
Inc Remained | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | +/- |  | Total (Last wk) |  | Total FP |  | Total Test Cases
Programming | 2024-08-20: 30x3; 2024-09-03: 0; 2024-09-17: 90; 2024-10-01: 102; 2024-10-15: 779; 2024-12-03: Open Issue (This wk); 2024-12-24: Remained (Last wk); 2025-01-14: New (This wk); 2025-02-04: Solved (This wk)
[16 empty] | 2 |  |  | 2 |  |  | 1 |  |  | 1
Programming Status (Function) | 2024-08-20: Result; 2024-10-01: Plan (Accm.); 2024-10-15: Progress (Days); 2024-10-29: Evaluation
| Accum. (This wk) |  | Accum. (Last wk) |  | Achieve (This wk) | [13 empty] | Route A (approved) | [5 empty] | Route B (approved)
Start | 2024-08-20: 19; 2024-09-03: 16; 2024-09-17: 3; 2024-10-01: 19; 2024-10-15: 0; 2024-10-29: B; 2024-12-24: Accum. (This wk); 2025-01-07: New (This wk); 2025-01-21: Accum. (Last wk); 2025-02-04: Accum. (This wk); 2025-02-18: New (This wk); 2025-03-04: Accum. (Last wk)
Finish | 2024-08-20: 16; 2024-09-03: 16; 2024-09-17: 0; 2024-10-01: 16; 2024-10-15: 0; 2024-10-29: B
Tested | 2024-08-20: 15; 2024-09-03: 10; 2024-09-17: 5; 2024-10-01: 15; 2024-10-15: 0; 2024-10-29: B; 2024-12-03: Change Request (PU); 2024-12-24: 0; 2025-01-07: 0; 2025-01-21: 0; 2025-02-04: 0; 2025-02-18: 0; 2025-03-04: 0
Total | 2024-08-20: 50; 2024-09-03: 42; 2024-09-17: 8; 2024-10-01: 50; 2024-10-15: 0; 2024-10-29: B
[16 empty] | Test Script Creation |  |  | Total Target Test Items |  |  | Created Test Items |  |  | % of Created
Quality | 2024-08-20: Accum Tested FP; 2024-09-03: Target per FP; 2024-09-17: Test Density (/FP); 2024-10-01: Inc Detection (/FP); 2024-10-15: Accum. (This wk); 2024-10-29: Accum. (Last wk); 2024-11-12: Achieve (This wk); 2024-12-03: IFT (Test case); 2024-12-24: 0; 2025-01-14: 0; 2025-02-04: 0%
[16 empty] | BCT (Test scenario) |  |  | 0 |  |  | 0 |  |  | 0%
Tested Cases (Screen) | 2024-08-20: 26.8; 2024-09-03: 10-14; 2024-09-17: 3.7313; 2024-10-15: 100; 2024-10-29: 81.5; 2024-11-12: 18.5
Tested Cases (Batch) | 2024-08-20: 66.9; 2024-09-03: 4-8; 2024-09-17: 3.3782; 2024-10-15: 226; 2024-10-29: 155; 2024-11-12: 71
Tested Cases (Report) | 2024-08-20: 7.5; 2024-09-03: 4-8; 2024-09-17: 4; 2024-10-15: 30; 2024-10-29: 0; 2024-11-12: 30
Incident Detect (Screen) | 2024-09-03: 3; 2024-10-01: 1.1567; 2024-10-15: 31; 2024-10-29: 22; 2024-11-12: 9
Incident Detect (Batch) | 2024-09-03: 2; 2024-10-01: 0.23916; 2024-10-15: 16; 2024-10-29: 16; 2024-11-12: 0
Incident Detect (Report) | 2024-09-03: 1.2; 2024-10-01: 0; 2024-10-15: 0; 2024-10-29: 0; 2024-11-12: 0
Incident Fixed (Screen) | 2024-10-15: 0; 2024-10-29: 0; 2024-11-12: 0
Incident Fixed (Batch) | 2024-10-15: 0; 2024-10-29: 0; 2024-11-12: 0
Incident Fixed (Report) | 2024-10-15: 0; 2024-10-29: 0; 2024-11-12: 0
UI/SS
A:Ahead of schedule
B:On schedule
C:Delay (less than 1 week)
D:Delay (over 1 week)
User Review
Issue and Countermeasure
1. Manual Deployment issue
Program
ming
(Indicator: Function)
Testing & Quality
(Indicator: Test Case)
TMT: TBOS
<Progress Status>
Programming and Unit Test (PU)
Start : Finish : Tested = 1 : 1 : 1
Vendor PIC
ISD PIC
Kanphong Sunon
DR
PU
1 Oct
IFT
BCT
BCT-IS
SIT
UT
IT
IP
Non Prod TASC
Integration
Prod TASC
Integration
Go-live
2-Mar
This week actions
1. Continue 1 PT-Test ,Finish Test 6 Function
2. Start Dev 3 Functions , Start Test 5 Functions
3. Create Folder and Upload Ctrl files TBOS server HULFT
4. Submit Response time to IS (Performance Test)
5. Deploy Developed Function to TBOS Dev , Plan 26/9/2024
6. Meeting with FCH for IFT,BCT Script Knowledge Transfer #1 30/9/2024
Next week actions
1. Finished PT- Test 4 Functions
2. Continue Dev 3 Functions , Start 4 Functions
3. Submit Sample NQC request interface 03 Oct
4. IFT Script Discussion with IS 04 Oct

## PB Curve
| 2024-08-20 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-02-11 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11
Remained Test Cases (plan) | 779 | 779 | 779 | 779 | 752 | 542 | 422 | 330 | 241 | 140 | 7 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27 | -27
Remained Test Cases (result) | 779 | 779 | 779 | 779 | 752 | 542 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422
Accum Test Cases (result) | 0 | 0 | 0 | 0 | 27 | 237 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357 | 357
Inc-Detected (standard) | 0 | 0 | 0 | 0 | 9 | 72 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108
Inc detected (accum) | 0 | 0 | 0 | 0 | 5 | 38 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
Inc fixed (accum) | 0 | 0 | 0 | 0 | 5 | 38 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
END
START
TODAY

## Usage Guideline
Phase |  |  |  |  | Project Name |  |  | TMAP Standard | [6 empty] | Page
Block Name |  |  |  |  | TMAP Management Standard |  |  |  |  | Function Name | 04 Progress Management | Created |  | 2007-04-02 | By | Rujipun
Document Name |  |  |  |  | Weekly Report PU |  |  |  |  | Title | Usage Guideline | Updated |  | 2009-09-04 | By | Anan
Usage Guideline : Weekly Report PU
| 1. | Template Layout
| 2. | How to Fill up
|  | 2.1 | Header
|  |  | Step 1 : | Fill in the project and System Name, e.g. TMAP-EM : FISM, TMAP Standards : Management Standard
|  |  | Step 2 : | Fill in the date of making the report. Date of making the report is usually the date of one day before the weekly progress meeting date.
|  |  | Step 3 : | Get the signature of Vendor PIC and ISD PIC of the project. Vendor PIC and ISD PIC are required to check the correctness of the progress report before signing.
|  | 2.2 | Overview Schedule
|  |  | Step 1 : | Fill in System Name
|  |  | Step 2 : | Draw overview schedule of the project for all phases
|  |  | Step 3 : | Update "Progress Line" to reflect and show the progress or delay of the project
|  | 2.3 | Programming Statistics
|  |  | Step 1 : | Fill in Report Creation Date. Usually, it is the date of one day before the weekly meeting date.
|  |  | Step 2 : | Fill in weekly plan (all weeks of the plan). The value to fill is the summation of all tasks measured in the unit of Indicator of the phase, and it can be obtained from
Total Plan row in Daily Progress Report, as an example displayed below:
|  |  |  | Daily Progress |  |  | :
Report
|  |  |  | Weekly |  |  | :
Report
For PU, there are three types of tasks, i.e. 1) Start Coding, 2) Finish Coding, and 3) Tested. Unit of Indicator of Coding is Function.
Note : TMAP Standard provides Daily Progress template for planning and tracking the progress. Please refer to the template.
|  |  | Step 3 : | Fill in weekly result (for the week to report). The value to fill is also the summation of all tasks measured in the unit of Indicator of the phase, and it can be
obtained from Total Result row in Daily Progress Report, as an example displayed below:
|  |  |  | Daily Progress |  |  | :
Report
|  |  |  | Weekly |  |  | :
Report
|  |  | Note-1 : | Workload Ratio of tasks is the ratio of workload of each task needed to be completed in order to finish the phase. In PU, there are three basic
tasks, i.e. 1) Start Coding, 2) Finish Coding, and 3) Tested. Here, we assume all tasks have the same workload in Standard. That means
Coding have the same workload as Testing.
|  |  | Note-2 : | In case that the phase is very short, this can be daily instead of weekly
|  |  | Note-3 : | Difference (weekly and accum), Plan (accum) and Result (accum) are automatically calculated
|  |  | Note-4 : | Accum Plan is equal to Accum Result when the phase is finished.
|  | 2.4 | Testing and Quality Statistics
|  |  | Step 1 : | Fill in Report Creation Date. Usually, it is the date of one day before the weekly meeting date.
|  |  | Step 2 : | Fill in weekly plan (all weeks of the plan). The value to fill is the number of test cases planned to test on that week , and it can be obtained from
Total Plan (Tested) row in Daily Progress Report, as an example displayed below:
|  |  |  | Daily Progress |  |  | :
Report
|  |  |  | Weekly |  |  | :
Report
|  |  | Step 3 : | Fill in weekly result (for the week to report). The value to fill is the number of test cases tested on that week , and it can be obtained from
Total Result (Tested) row in Daily Progress Report, as an example displayed below:
|  |  |  | Daily Progress |  |  | :
Report
|  |  |  | Weekly |  |  | :
Report
|  |  | Step 4 : | Fill in incident detected in the week.
|  |  | Step 5 : | Fill in incident fixed in the week.
|  |  | Note-1 : | Test plan (accum), Test Result (accum), Test Plan (remained) and Test Result (remained) are automatically calculated.
|  |  | Note-2 : | Incident Detected (accum), Incident Fixed (accum) and Incident Remained are automatically calculated.
|  | 2.5 | Progress Status
|  |  | Step 1 : | Fill in current total number of tasks. In PU the unit of indicator is Function. And there are three types of tasks, i.e. 1) Start Coding,
2) Finish Coding, and 3) Tested. For example, if there are 61 functions, Total = 61x3
|  |  | Step 2 : | Fill in adjustment value of tasks. For example, if we add 1 function to the current 61 functions system, the +/- column will be filled in by +3 (1 x 3).
If we delete 1 function, the +/- column will be filled in by -3 (-1x3).
|  |  | Step 3 : | Fill in the total number of tasks of last week.
|  |  | Step 4 : | Fill in total FP. Total FP can be obtained from function list.
|  |  | Step 5 : | Fill in the number of total test cases.
|  |  | Step 6 : | Fill in the accumulated actual results of tasks finished last week for each type of tasks.
|  |  | Step 7 : | Fill in the results of tasks achieved this week for each type of tasks, and these values can be obtained from Result Weekly Summary row of Daily Progress Report.
For example,
Task: Tested
[9 empty] | Daily Progress Report |  |  |  | Weekly Report
|  |  | Step 8 : | Fill in the accumulated plan until this week. This value can be obtained from Plan Weekly Summary row of Daily Progress Report.
For example,
Task: Tested
[9 empty] | Daily Progress Report |  |  |  | Weekly Report
|  |  | Step 9 : | Fill in the progress status of each type of tasks in days. Positive (+) means it is advanced. Negative (-) means it is delayed.
- The progress will use the worst case. If it is delay, it uses the longest delay days from plan. For example, if there are two functions,
the first one delays two days and the second one delays ten days. The progress status will be -10.
As for advance, it uses the shortest advanced days.
- To count number of days for delay of a function, we count from the day to do it in plan until the day we write a weekly report;
not count holidays. For example, we plan to finish a function in Day-1, but we have not finished it. On the end of Day-3,
we make a weekly report, so this function will delay 3 days -- Day-1, Day-2 and Day-3. As for advance, it is the opposite of dalay,
counting from report creating day to the day of plan.
|  |  | Step 10 : | Fill in Evaluation : A = Ahead of schedule, B = On schedule, C = Delay (less than 1 week), D = Delay (over 1 week).
|  |  | Step 11 : | Fill in Accum tested FP for each type of functions. Accum tested FP can be tracked by Daily Plan (progress)
|  |  | Step 12 : | Fill in Accum tested items, detected incidents, and fixed incidents of last week
|  |  | Step 13 : | Fill in tested items, detected incidents, and fixed incidents of this week.
|  |  | Step 14 : | Fill in the number of remained issues of last week.
|  |  | Step 15 : | Fill in the number of new issues found in this week.
|  |  | Step 16 : | Fill in the number of issues resolved this week.
|  |  | Step 17 : | Fill in CR Route A's Accum CRs of this week. Here, we count only the approved CRs. For the details of CRs, they are tracked by CR list and form.
|  |  | Step 18 : | Fill in CR Route A's Accum CRs of last week.
|  |  | Step 19 : | Fill in CR Route B's Accum CRs of this week.
|  |  | Step 20 : | Fill in CR Route B's Accum CRs of last week.
|  |  | Step 21 : | Fill in total target test cases of IFT
|  |  | Step 22 : | Fill in created test cases of IFT
|  |  | Step 23 : | Fill in total target test scenarios of BCT
|  |  | Step 24 : | Fill in created test scenarios of BCT
|  |  | Note-1 : | Result of accumulated tasks achieved this week is automatically calculated.
|  |  | Note-2 : | Test density ratio is automatically calculated.
|  |  | Note-3 : | Incident detection ratio is automatically calculated.
|  |  | Note-4 : | Automatically calculated for Accum Tested, incident detected&fixed of this week
|  |  | Note-5 : | Open issue (this week) is automatically calculated. It is remained issues (last week) + New issues (this week) - Solved issues (this week).
|  |  | Note-6 : | Automatically calculated % of Created test items for IFT and BCT
|  |  | Note-7 : | Automatically calculated = CR Route A's Accum CRs (This wk) - CR Route A's Accum CRs (Last wk)
|  |  | Note-8 : | Automatically calculated = CR Route B's Accum CRs (This wk) - CR Route B's Accum CRs (Last wk)
|  | 2.6 | Actions and Main Issues
|  |  | Step 1 : | Fill in this week actions
|  |  | Step 2 : | Fill in next week planned-to-do actions.
|  |  | Step 3 : | Fill in issue and its countermeasure. Only important issues that need management concerns.
Note : Delay of project is also considered to be an issue and needed to provide the countermeasure of it.
Header
Overview Schedule
Testing & Quality Statistics
Progress Status, Quality, Actions and Issues
Footer
On schedule
Delay
Ahead of Schedule
Programming Statistics
Step 1: Project and System Name
Step 2: Date of Making the report
Step 3: Signature of Vendor PIC and ISD PIC of the Project.
Step 1: System Name
Step 2: Draw overview schedule of the project for all phases
Step 3: Update "Progress Line" to reflect and show the progress or delay of the project
Note-1: Workload ratio of tasks
Step 1: Report Creation Date (one day before weekly meeting)
Note-4: Accum Plan = Accum Result when the phase is finished
Step 2: Fill in weekly plan (summation of all tasks)
Step 3: Fill in weekly result (summation of all tasks)
Note-3: Difference (weekly and accum), Plan (accum) and Result (accum) are automatically calculated
Note-2: In case that the phase is very short, this can be daily instead of weekly
Step 1: Report Creation Date (one day before weekly meeting)
Step 2: Fill in weekly plan for testing
Step 3: Fill in weekly result for testing
Note-2: Accum Incident detected&fixed and Incident remained are automatically calculated
Step 4: Fill in Incident detected in the week
Step 5: Fill in Incident fixed in the week
Note-1: Accum test plan&result and remained test plan&result are automatically calculated
Step 1: Fill in current total tasks
Step 2: Fill in adjustment values of tasks (increase/ decrease)
Note-1: Automatically calculated = Accum (Last wk) + Achieve (This wk)
Step 3: Fill in total tasks of last week
Step 6: Fill in result of Accum. (Last wk)
Step 7: Fill in result of achieve (This wk)
Step 8: Fill in accum plan of this week
Step 9: Fill in Progress (+ advance, - delay)
Step 10: Fill in Evaluation (A,B,C,D : see meaning above)
Note-5: Automatically calculated = Remained (Last wk) + New (This wk) - Solved (This wk)
Step 14: Fill in Remained issue of last week
Step 15: Fill in new issues found this week
Step 16: Fill in issues resolved this week
Step 17: Fill in CR Form A's Accum CRs of this week
Step 18: Fill in CR Form A's Accum CRs of last week
Step 19: Fill in CR Form B's Accum CRs of this week
Step 20: Fill in CR Form B's Accum CRs of last week
Step 4: Fill in total FP
Step 5: Fill in total test cases
Step 11: Fill in Accum Tested FP for each type of functions
Step 12: Fill in Accum Tested, incident detected&fixed of last week
Note-2: Automatically calculated for test density
Note-3: Automatically calculated for incident detection
Note-4: Automatically calculated for Accum Tested, incident detected&fixed of this week
Step 13: Fill in Tested, incident detected&fixed achieved this week
Step 1: Fill in this week actions
Step 2: Fill in next week planned-to-do actions
Step 3: Fill in issue and its countermeasure
(Only important issues that need management concerns
Step 21: Fill in total target test cases of IFT
Step 22: Fill in created test cases of IFT
Step 23: Fill in total target test scenarios of BCT
Note-6: Automatically calculated % of Created test items for IFT and BCT
Step 24: Fill in created test scenarios of BCT
Note-7: Automatically calculated = CR Route A's Accum CRs (This wk) - CR Route A's Accum CRs (Last wk)
Note-8: Automatically calculated = CR Route B's Accum CRs (This wk) - CR Route B's Accum CRs (Last wk)
Current Weekly Meeting Date
Current Weekly Meeting Date

## PB Curve Guideline
PU Weekly Report Guideline
[How to understand PB Curve]
In the software development, we wish to have the incident detected curve as shown in Figure 1, while we plan to test the application in three steps
at different test rates, i.e. 1) Learning Period: the rate of testing is slow in order to prepare, learn, and get used to the testing, 2) Adjusted Period:
the rate of testing is in full speed, 3) Fixing Period: the rate of testing is slow down in order to have time for fixing incidents.
[7 empty] | 2005-06-13 | 2005-06-20 | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08 | 2005-08-15 | 2005-08-22 | 2005-08-29 | 2005-09-05 | 2005-09-12 | 2005-09-19
[6 empty] | Remained Test Cases (plan) | 300 | 290 | 280 | 270 | 240 | 210 | 180 | 150 | 120 | 90 | 60 | 30 | 20 | 10 | 0
[6 empty] | Incident detected (accum) | 0 | 1 | 2 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 28 | 29 | 30
However, in the actual situation the curves are various and different from the ideal. We can draw these curves, see the tendency and compare with
the standard curve in order to predict and be alerted for the possible problems and control the software quality. We call these curves "PB Curve".
PB curve is used to see the tendency of developed software in terms of the number of test cases and the number of incidents. Normally, it consists
of four graphs, i.e. 1) Remained Test Cases (plan), 2) Remained Test Cases (result), 3) Incident detected (standard), and 4) Incident detected
(accum). But in TMAP weekly report, "Incident Fixed (accum)" is added to show the tendency of fixing the incidents.
[7 empty] | 2005-06-13 | 2005-06-20 | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08 | 2005-08-15 | 2005-08-22 | 2005-08-29 | 2005-09-05 | 2005-09-12 | 2005-09-19
[6 empty] | Remained Test Cases (plan) | 300 | 300 | 280 | 265 | 245 | 215 | 200 | 175 | 140 | 110 | 65 | 35 | 10 | 0 | 0
[6 empty] | Remained Test Cases (result) | 300 | 300 | 294 | 288 | 267 | 230 | 205 | 173 | 137 | 105 | 70 | 36 | 12 | 12 | 12
[6 empty] | Accum Test Cases (plan) | 0 | 0 | 20 | 35 | 55 | 85 | 100 | 125 | 160 | 190 | 235 | 265 | 290 | 300 | 300
[6 empty] | Inc-Detected (standard) | 0 | 0 | 5 | 9 | 13 | 20 | 23 | 29 | 37 | 44 | 55 | 61 | 67 | 69 | 69
[6 empty] | Inc detected (accum) | 0 | 0 | 1 | 3 | 5 | 7 | 22 | 38 | 45 | 46 | 52 | 65 | 72 | 72 | 72
[6 empty] | Inc fixed (accum) | 0 | 0 | 0 | 2 | 4 | 7 | 13 | 23 | 32 | 43 | 48 | 58 | 70 | 70 | 70
[Standard Quality Indicator]
The PU standard quality indicators are shown as follows:
FP Base for Batch, Screen, and Report -- per FP
|  | Batch | Quality verification |  | Test Case
|  | (1FP=200 Step) |  | Case/FP | 6+/-2 (4-8)
|  |  | Quality Indicator | Incident/FP | 2
|  | Screen | Quality verification |  | Test Case
|  |  |  | Cases | 12+/-2 (10-14)
|  |  | Quality Indicator | Incidents | 3
|  | Report | Quality verification |  | Test Case
|  | Normal |  | Cases | 6+/-2 (4-8)
|  |  | Quality Indicator | Incidents | 1.2
|  | Report | Quality verification |  | Test Case
|  | Complex |  | Cases | 12+/-2 (10-14)
|  |  | Quality Indicator | Incidents | 2.4
End
Start
Adjusted Period
Learning Period
Fixing Period
50% Period of time
50% Period of time
Figure 1: Ideal Incident Detected Curve VS Planned Test Cases Curve
Phase
Block Name
Document Name
PU Weekly Report
Project Name
TMAP Standard
Function Name
Title
PU Weekly Report Guideline
23/6/2006
Created
Updated
Page
By
By
Rujipun
End
Start
＜Causes of testing behind schedule＞
・There are too many incidents.
・Person in charge hasn’t enough skill.
・Test environment isn’t perfect .
・Lack of concentration in testing.
・The frequency of specification change
・Insufficient man power （Imperfect plan of man power）
＜In case of too many incidents＞
・There is problem on quality
・Planned target is too low
＜In case of too low incidents＞
・Test items are not enough, some test items are missing.
・Test cases are not appropriate.
<Tendency of Incident Fixing>
Incident fixing tends to finish by the end of testing phase.
Today
＜In case, test is almost finished but incident detection still high.＞
・Side effect incidents are detected due to incomplete of incident fixing and specification change

## Example_Weekly Report
As of Date: 2005/10/3
| 2006-01-01 |  | 2006-02-01 |  | 2006-03-04 |  | 2006-04-04 |  | 2006-05-05 |  | 2006-06-05 |  | 2006-07-06 |  | 2006-08-06 |  | 2006-09-06 |  | 2006-10-07 |  | 2006-11-07 |  | 2006-12-08 |  | 2007-01-08
XXX System
wk ended | 2005-06-13 | 2005-06-20 | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08 | 2005-08-15 | 2005-08-22 | 2005-08-29 | 2005-09-05 | 2005-09-12 | 2005-09-19 | 2005-09-26 | 2005-10-03 | 2005-10-10 | 2005-10-17 | 2005-10-24 | 2005-10-31 | 2005-11-07 | 2005-11-14 | 2005-11-21 | 2005-11-28 | 2005-12-05 | 2005-12-12 | 2005-12-19 | 2005-12-26 | 2006-01-02
Plan (weekly) | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 24 | 18 | 21 | 18 | 24 | 21 | 24 | 21 | 12 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Result (weekly) | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 24 | 18 | 24 | 24 | 15 | 21 | 27 | 24 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Difference (weekly) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | -9 | 0 | 3 | 3 | -1 | -7 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan (accum.) | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 33 | 51 | 72 | 90 | 114 | 135 | 159 | 180 | 192 | 207 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219
Result (accum.) | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 33 | 51 | 75 | 99 | 114 | 135 | 162 | 186 | 197 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205
Difference (accum.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9 | 0 | 0 | 3 | 6 | 5 | -2 | -14 | -14 | -14 | -14 | -14 | -14 | -14 | -14 | -14 | -14 | -14 | -14 | -14
| 2005-06-13 | 2005-06-20 | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08 | 2005-08-15 | 2005-08-22 | 2005-08-29 | 2005-09-05 | 2005-09-12 | 2005-09-19 | 2005-09-26 | 2005-10-03 | 2005-10-10 | 2005-10-17 | 2005-10-24 | 2005-10-31 | 2005-11-07 | 2005-11-14 | 2005-11-21 | 2005-11-28 | 2005-12-05 | 2005-12-12 | 2005-12-19 | 2005-12-26 | 2006-01-02
Test Plan (weekly) | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 25 | 30 | 130 | 125 | 160 | 250 | 120 | 120 | 180 | 110 | 150
Test Result (weekly) | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 25 | 30 | 130 | 125 | 160 | 250 | 120 | 120 | 180 | 90 | 0
Test Plan (accum.) | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 41 | 71 | 201 | 326 | 486 | 736 | 856 | 976 | 1156 | 1266 | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1416
Test Result (accum.) | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 41 | 71 | 201 | 326 | 486 | 736 | 856 | 976 | 1156 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246
Test Plan (remained) | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1400 | 1375 | 1345 | 1215 | 1090 | 930 | 680 | 560 | 440 | 260 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test Result (remained) | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1400 | 1375 | 1345 | 1215 | 1090 | 930 | 680 | 560 | 440 | 260 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170
Inc Detected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 13 | 25 | 31 | 38 | 43 | 20 | 55 | 42 | 0
Inc Fixed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 10 | 26 | 23 | 8 | 71 | 29 | 46 | 39 | 0
Inc Detected (accum.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 23 | 48 | 79 | 117 | 160 | 180 | 235 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277
Inc Fixed (accum.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 19 | 45 | 68 | 76 | 147 | 176 | 222 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261
Inc Remained | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 | 11 | 41 | 13 | 4 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
| Total |  | +/- |  | Total (Last wk) |  | Total FP |  | Total Test Cases
Programming | 2005-06-13: 73x3; 2005-06-27: 0; 2005-07-11: 219; 2005-07-25: 130; 2005-08-08: 1416; 2005-09-26: Open Issue (This wk); 2005-10-17: Remained (Last wk); 2005-11-07: New (This wk); 2005-11-28: Solved (This wk)
[16 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
Programming Status (Function) | 2005-06-13: Result; 2005-07-25: Plan (Accm.); 2005-08-08: Progress (Days); 2005-08-22: Evaluation
| Accum. (This wk) |  | Accum. (Last wk) |  | Achieve (This wk) | [13 empty] | Route A (approved) | [5 empty] | Route B (approved)
Start | 2005-06-13: 69; 2005-06-27: 67; 2005-07-11: 2; 2005-07-25: 69; 2005-08-08: 0; 2005-08-22: B; 2005-10-17: Accum. (This wk); 2005-10-31: New (This wk); 2005-11-14: Accum. (Last wk); 2005-11-28: Accum. (This wk); 2005-12-12: New (This wk); 2005-12-26: Accum. (Last wk)
Finish | 2005-06-13: 69; 2005-06-27: 67; 2005-07-11: 2; 2005-07-25: 69; 2005-08-08: 0; 2005-08-22: B
Tested | 2005-06-13: 67; 2005-06-27: 63; 2005-07-11: 4; 2005-07-25: 69; 2005-08-08: -1; 2005-08-22: C; 2005-09-26: Change Request (PU); 2005-10-17: 0; 2005-10-31: 0; 2005-11-14: 0; 2005-11-28: 0; 2005-12-12: 0; 2005-12-26: 0
Total | 2005-06-13: 205; 2005-06-27: 197; 2005-07-11: 8; 2005-07-25: 207; 2005-08-08: -1; 2005-08-22: C
[16 empty] | Test Script Creation |  |  | Total Target Test Items |  |  | Created Test Items |  |  | % of Created
Quality | 2005-06-13: Accum Tested FP; 2005-06-27: Target per FP; 2005-07-11: Test Density (/FP); 2005-07-25: Inc Detection (/FP); 2005-08-08: Accum. (This wk); 2005-08-22: Accum. (Last wk); 2005-09-05: Achieve (This wk); 2005-09-26: IFT (Test case); 2005-10-17: 100; 2005-11-07: 30; 2005-11-28: 30%
[16 empty] | BCT (Test scenario) |  |  | 50 |  |  | 4 |  |  | 8%
Tested Cases (Screen) | 2005-06-13: 100; 2005-06-27: 10-14; 2005-07-11: 10.8; 2005-08-08: 1080; 2005-08-22: 1020; 2005-09-05: 60
Tested Cases (Batch) | 2005-06-13: 10; 2005-06-27: 4-8; 2005-07-11: 5.4; 2005-08-08: 54; 2005-08-22: 40; 2005-09-05: 14
Tested Cases (Report) | 2005-06-13: 20; 2005-06-27: 4-8; 2005-07-11: 5.6; 2005-08-08: 112; 2005-08-22: 96; 2005-09-05: 16
Incident Detect (Screen) | 2005-06-27: 3; 2005-07-25: 1.8; 2005-08-08: 180; 2005-08-22: 152; 2005-09-05: 28
Incident Detect (Batch) | 2005-06-27: 2; 2005-07-25: 2.7; 2005-08-08: 27; 2005-08-22: 23; 2005-09-05: 4
Incident Detect (Report) | 2005-06-27: 1.2; 2005-07-25: 3.5; 2005-08-08: 70; 2005-08-22: 60; 2005-09-05: 10
Incident Fixed (Screen) | 2005-08-08: 166; 2005-08-22: 142; 2005-09-05: 24
Incident Fixed (Batch) | 2005-08-08: 27; 2005-08-22: 20; 2005-09-05: 7
Incident Fixed (Report) | 2005-08-08: 68; 2005-08-22: 60; 2005-09-05: 8
UI/SS
This week actions
1) Started and finished programming 2 functions, and tested 4 functions
--> Accum result / Accum plan = 205 / 207 = 99.03%
--> Accum result / Total = 205 / 219 = 93.60%
--> Accum tested items / Accum plan = 1246 / 1266 = 98.42%
--> Accum tested items / Total = 1246 / 1416 = 87.99%
Next week actions
1) Start and finish programming 4 functions, and test 6 functions.
2) Fix 16 remained bugs.
A:Ahead of schedule
B:On schedule
C:Delay (less than 1 week)
D:Delay (over 1 week)
User Review
Issue and Countermeasure
Program
ming
(Indicator: Function)
Testing & Quality
(Indicator: Test Case)
TMAP: XXX
<Progress Status>
Programming and Unit Test (PU)
Start : Finish : Tested = 1 : 1 : 1
Oct-3
UR
DR
DN
PU
ST
UT
TR
IP
Vendor PIC
ISD PIC

## Example_PB Curve
| 2005-06-13 | 2005-06-20 | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08 | 2005-08-15 | 2005-08-22 | 2005-08-29 | 2005-09-05 | 2005-09-12 | 2005-09-19 | 2005-09-26 | 2005-10-03 | 2005-10-10 | 2005-10-17 | 2005-10-24 | 2005-10-31 | 2005-11-07 | 2005-11-14 | 2005-11-21 | 2005-11-28 | 2005-12-05 | 2005-12-12 | 2005-12-19 | 2005-12-26 | 2006-01-02
Remained Test Cases (plan) | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1400 | 1375 | 1345 | 1215 | 1090 | 930 | 680 | 560 | 440 | 260 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remained Test Cases (result) | 1416 | 1416 | 1416 | 1416 | 1416 | 1416 | 1400 | 1375 | 1345 | 1215 | 1090 | 930 | 680 | 560 | 440 | 260 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170
Accum Test Cases (result) | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 41 | 71 | 201 | 326 | 486 | 736 | 856 | 976 | 1156 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246 | 1246
Inc-Detected (standard) | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 15 | 43 | 69 | 103 | 156 | 181 | 207 | 245 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264
Inc detected (accum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 23 | 48 | 79 | 117 | 160 | 180 | 235 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277 | 277
Inc fixed (accum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 19 | 45 | 68 | 76 | 147 | 176 | 222 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261
END
START
TODAY